## Tasks
task_id | project_id | task_name | employee_id | priority | start_date | due_date | status
1001 | 201 | UI Design | 104 | High | 2026-06-03 | 2026-06-15 | Completed
1002 | 201 | Database Design | 103 | High | 2026-06-05 | 2026-06-20 | Completed
1003 | 201 | API Development | 101 | High | 2026-06-15 | 2026-07-10 | In Progress
1004 | 201 | API Testing | 102 | Medium | 2026-07-10 | 2026-07-20 | Pending
1005 | 201 | Payment Integration | 105 | High | 2026-07-15 | 2026-08-05 | Delayed
1006 | 202 | Requirement Analysis | 108 | High | 2026-05-16 | 2026-05-25 | Completed
1007 | 202 | Database Development | 106 | High | 2026-05-26 | 2026-06-15 | Completed
1008 | 202 | Backend Development | 105 | High | 2026-06-10 | 2026-07-15 | In Progress
1009 | 202 | Frontend Development | 101 | Medium | 2026-06-20 | 2026-07-25 | In Progress
1010 | 202 | System Testing | 107 | High | 2026-07-20 | 2026-08-05 | Delayed
1011 | 203 | UI Development | 104 | Medium | 2026-04-12 | 2026-05-10 | Completed
1012 | 203 | Product Catalog | 108 | High | 2026-04-20 | 2026-05-20 | Completed
1013 | 203 | Payment Gateway | 105 | High | 2026-05-01 | 2026-06-01 | Completed
1014 | 203 | Order Management | 101 | Medium | 2026-05-15 | 2026-06-15 | Completed
1015 | 203 | Final Testing | 107 | High | 2026-06-15 | 2026-07-10 | Completed
1016 | 204 | Requirement Gathering | 108 | High | 2026-06-21 | 2026-07-05 | Completed
1017 | 204 | Employee Database | 103 | High | 2026-07-01 | 2026-07-25 | In Progress
1018 | 204 | Attendance Module | 101 | Medium | 2026-07-10 | 2026-08-05 | In Progress
1019 | 204 | Leave Management | 105 | Medium | 2026-07-15 | 2026-08-15 | Pending
1020 | 204 | System Testing | 107 | High | 2026-08-01 | 2026-08-25 | Pending
1021 | 205 | Data Collection | 106 | High | 2026-07-02 | 2026-07-15 | Completed
1022 | 205 | Data Cleaning | 103 | High | 2026-07-10 | 2026-07-25 | Completed
1023 | 205 | KPI Development | 106 | High | 2026-07-20 | 2026-08-10 | In Progress
1024 | 205 | Dashboard Design | 104 | Medium | 2026-07-25 | 2026-08-15 | In Progress
1025 | 205 | Performance Analysis | 103 | High | 2026-08-01 | 2026-08-20 | Pending
1026 | 206 | UI Design | 104 | Medium | 2026-05-26 | 2026-06-10 | Completed
1027 | 206 | Payment API | 105 | High | 2026-06-05 | 2026-06-25 | Completed
1028 | 206 | Security Testing | 107 | High | 2026-06-20 | 2026-07-15 | Completed
1029 | 206 | Mobile Testing | 102 | Medium | 2026-07-10 | 2026-08-01 | Delayed
1030 | 206 | Final Deployment | 101 | High | 2026-08-01 | 2026-08-20 | In Progress

## Employees
employee_id | employee_name | department | role
101 | Rahul Sharma | Development | Developer
102 | Priya Mehta | Testing | QA Engineer
103 | Amit Patil | Data | Data Analyst
104 | Neha Singh | Design | UI/UX Designer
105 | Vikram Joshi | Development | Backend Developer
106 | Sneha Kulkarni | Data | Data Engineer
107 | Arjun Shah | Testing | QA Engineer
108 | Pooja Desai | Product | Product Analyst

## Projects
project_id | project_name | client | start_date | deadline | status
201 | Banking App | FinCorp | 2026-06-01 | 2026-09-30 | In Progress
202 | CRM Platform | SalesPro | 2026-05-15 | 2026-08-31 | In Progress
203 | E-Commerce Portal | ShopKart | 2026-04-10 | 2026-07-31 | Completed
204 | HR Management System | PeopleFirst | 2026-06-20 | 2026-10-15 | In Progress
205 | Analytics Dashboard | DataCore | 2026-07-01 | 2026-09-15 | In Progress
206 | Mobile Payment App | PayWorld | 2026-05-25 | 2026-08-20 | In Progress

## Employee Workload
employee_id | total_tasks | employee_name | department | role
101 | 5 | Rahul Sharma | Development | Developer
105 | 5 | Vikram Joshi | Development | Backend Developer
104 | 4 | Neha Singh | Design | UI/UX Designer
103 | 4 | Amit Patil | Data | Data Analyst
107 | 4 | Arjun Shah | Testing | QA Engineer
106 | 3 | Sneha Kulkarni | Data | Data Engineer
108 | 3 | Pooja Desai | Product | Product Analyst
102 | 2 | Priya Mehta | Testing | QA Engineer

## Project Performance
project_id | project_name | client | total_tasks | completed_tasks | delayed_tasks | completion_rate
203 | E-Commerce Portal | ShopKart | 5 | 5 | 0 | 100
206 | Mobile Payment App | PayWorld | 5 | 3 | 1 | 60
202 | CRM Platform | SalesPro | 5 | 2 | 1 | 40
201 | Banking App | FinCorp | 5 | 2 | 1 | 40
205 | Analytics Dashboard | DataCore | 5 | 2 | 0 | 40
204 | HR Management System | PeopleFirst | 5 | 1 | 0 | 20

## Dashboard
PRODUCT OPERATIONS & PERFORMANCE DASHBOARD |  |  |  |  | Status | Task Count | Employee Name | Total Tasks
[5 empty] | Complted | 15 | Rahul Sharma | 5
[5 empty] | In Progress | 8 | Vikram Joshi | 5
| TOTAL TASKS | COMPLETED TASKS | DELAYED TASKS | COMPLETION RATE | Pending | 4 | Neha Singh | 4
| 30 | 15 | 3 | 50% | Delayed | 3 | Amit Patil | 4
[7 empty] | Arjun Shah | 4
[7 empty] | Sneha Kulkarni | 3
[7 empty] | Pooja Desai | 3
[7 empty] | Priya Mehta | 2